Statement of Work

EBS AP Invoice Automation Agent · Syntax Corporation · Syntax Corporation © 2026 · Confidential

1. Business problem

AP automation is a $3B+ category with multiple unicorns. Every EBS shop runs tens of thousands to millions of invoices a year — and pays incumbents $3–8 each.

- $12–15 — fully-loaded cost to process one invoice by hand

- 8–10 days — typical cycle time — late payments, missed discounts

- 1–3% — of spend lost to duplicate and over-billed invoices

2. Solution

- Reads any invoice: PDF, email or text — a deterministic parser (zero external deps) with an optional LLM for messy/scanned docs.

- Checks live EBS: Supplier, PO, receipts, tax and GL — read-only, org-scoped lookups against the real E-Business Suite.

- Matches & codes: Deterministic 3-way match with price/qty tolerances, GL distribution inheritance and tax classification.

- Validates & delivers: A QA gate proves every invoice balances before it writes balanced AP Open Interface files.

Same agentic pattern as Oracle's Private Agent Factory contract-renewal blog — pointed at the far larger AP revenue pool.

3. Value proposition

Estimated annual value ~$930,000; first-year net ~$822,520; payback ~1.4 months; 20–40× return on the agent fee.

- Processing cost: $475K / yr

- Early-pay discounts: $225K / yr

- Duplicate prevention: $150K / yr

- Audit / compliance: $80K / yr

4. Functional flow

5. Technical architecture

6. Scope & deliverables

- XXPAF PL/SQL package deployed to EBS 19c

- PAF agent (.paf import + canvas) + managed-MCP tool registration

- QA pack (tests + QA_REPORT) and technical design document

- Go-live support and knowledge transfer

7. Ongoing governance deliverables

- KPI / monitoring dashboard (throughput, STP %, exception rate) via the published REST API

- Exception-review console for HOLD / needs-approval invoices (human-in-the-loop)

- Model & prompt management — versioned prompts, model pinning, regression checks

- Periodic accuracy review — re-run the validation gate on a sampled set each quarter

- Change & incident management — controlled prompt/tool changes; severity-based incident handling

- Quarterly value review — realized savings vs the ROI model; tuning backlog

8. Implementation timeline

Target duration: 8 weeks.

| Phase | Weeks | Outcomes |
| --- | --- | --- |
| Discovery | 1–2 | Confirm volumes, invoice mix, target OU; finalize spec.yaml; access + Database Tools Connection |
| Build | 3–5 | XXPAF PL/SQL + managed-MCP tools; agent flowGraph; deliverables generated |
| Validate | 6 | Validation gate on ground-truth set; Python↔PL/SQL parity; zero unsafe actions |
| Go-live | 7 | Import .paf, rebind MCP + LLM, UAT, scheduled Open Interface Import |
| Hypercare | 8 | Monitored run, exception triage, KT; transition to managed services |

9. RACI matrix

| Activity | Syntax | Customer |
| --- | --- | --- |
| Discovery & spec sign-off | R/A | C |
| EBS access / Database Tools Connection | C | R/A |
| XXPAF PL/SQL build + deploy | R | A |
| Managed-MCP tool registration | R | C |
| Agent build + .paf import | R | C |
| Validation-gate execution | R | C |
| UAT & acceptance | C | R/A |
| Go-live & scheduling | R | A |
| Ongoing managed services | R | C |
| Security / change approvals | C | R/A |

10. Service levels (SLAs)

| Metric | Target |
| --- | --- |
| Agent service availability | 99.5% monthly (excl. EBS/OCI maintenance) |
| P1 (service down) response / resolution | 1 hr / 8 business hrs |
| P2 (degraded) response / resolution | 4 business hrs / 2 business days |
| P3 (question / minor) response | 1 business day |
| Support hours | 8×5 (24×7 optional) |
| QA-gate pass on accepted invoices | 100% balanced + reconciled before load |
| Extraction accuracy (sampled) | ≥ 98% on in-scope document types |

11. Entitlements

| Item | Included |
| --- | --- |
| Agent license | 1 production agent (this domain); add-on agents priced separately |
| Environments | Production + one non-prod (UAT) |
| Included run hours | 40 hrs/month managed-services run team |
| Updates & upgrades | Prompt / model / tool updates + PAF-release compatibility |
| Support tier | Standard 8×5 (per SLA table); premium 24×7 optional |
| Documentation | Installation, technical design, validation gate, QA report |

12. Pricing

Implementation (fixed fee, blended $95/hr, 320 hrs):

| Item | Amount |
| --- | --- |
| Implementation (~320 hrs @ $95 blended) | $30,400 |

Managed services (per month, by commitment term — medium tier):

| Term | Monthly | Discount |
| --- | --- | --- |
| 12 months | $8,957 | — |
| 24 months | $8,061 | 10% |
| 36 months | $7,165 | 20% |

13. OCI Bill of Materials

| Component | Pricing model | Notes |
| --- | --- | --- |
| Autonomous AI Database 26ai (ADB, ECPU) | License Included or BYOL (~76% lower) | PAF sidecar host |
| Oracle Private Agent Factory | $0 | included with AI Database 26ai |
| OCI Database Tools / Managed MCP | consumption (confirm at install) | replaces self-hosted broker |
| OCI Generative AI | per-token | model-dependent (extraction) |
| OCI Document Understanding (OCR) | per-page (optional) | only if PDF/scan ingestion |
| Compute / storage / networking | consumption | no broker VM; no Instant Client host |
| EBS 19c (OCI DBaaS/Exadata) | customer existing license | system of record + XXPAF logic |

14. Acceptance & assumptions

Acceptance: a green live golden test plus a balanced interface load in customer UAT.

This generic SOW shell is subject to the parties' MSA; have counsel review before use.

15. Signatures

| For Customer | For Syntax Corporation |
| --- | --- |
| Name: | Name: |
| Title: | Title: |
| Signature / Date: | Signature / Date: |

Syntax Corporation © 2026 · Confidential